## Task List
TASK | STATUS | PRIORITY | DUE DATE | ASSIGNED TO | DELIVERABLE

## Quote Templates
Quote Template Name | Company ID | Category | Template Description | Type | CreatedBy | Action | Description | Status | New Quote Template Name | Quote Notes | Order Porter | Tab Grid Layout | PDF | Load Form Configuration | Tab Structure | Deployment Date
AM - Block of Hours - Actual Rates | MPC | NRR | Block of Hours (Actual Rates) | Standard |  | Modify | Revised | Waiting | MPC - NRR - Block of Hours (Actual Rates) | Utilized for managing Non-Recurring Revenue (NRR) actual rates within a fixed block of hours. | Revision Needed | Complete | Pending | Complete | Pending
AM - Block of Hours - Blended Rates | MPC | NRR | Block of Hours (Blended Rates) | Standard |  | Keep | Revised | Waiting | MPC - NRR - Block of Hours (Blended Rates) | Used to manage Non-Recurring Revenue (NRR) with blended rates within a designated block of hours. | Revision Needed | Complete | Pending | Complete | Pending
AM - NRR |  | NRR | - | Standard |  | Delete | Training/descriptive template |  | - NRR - - | Training/descriptive template | Approved | Approved | Approved | Approved | Approved
AM - Time and Materials (TnM) - STD | MPC | NRR | Time and Materials (TnM) | Standard |  | Keep | Revised | Waiting | MPC - NRR - Time and Materials (TnM) | Used for managing Non-Recurring Revenue (NRR) on a time and materials basis, where charges are applied according to the actual time spent and materials used on a project. | Revision Needed | Complete | Pending | Complete | Pending
Annual NRR Upfront Pay | MPC | NRR | Upfront (Annual) Pay | Standard |  | Modify | Revised | Waiting | MPC - NRR - Upfront (Annual) Pay | Used for the management of Non-Recurring Revenue (NRR) involving annual licenses paid upfront. | Revision Needed | Complete | Pending | Complete | Pending
Change Order | MPC | NRR/MRR | Change Order | Standard |  | Modify | Revised | Waiting | MPC - NRR/MRR - Change Order | Used for processing change orders within a hybrid model of Monthly Recurring Revenue (MRR) and Non-Recurring Revenue (NRR). | Revision Needed | Complete | Pending | Complete | Pending
F1 GCC High Licenses - Add On Orders | GOV | NRR | GCC High Licenses (Add On Orders) | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - GCC High Licenses (Add On Orders) | Utilized for managing government clients who require additional GCC High licenses. | Revision Needed | Complete | Pending | Complete | Pending
F1 GCC High Licenses / Contract - Addendum | GOV | NRR | GCC High Licenses (Contract Addendum) | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - GCC High Licenses (Contract Addendum) | Used specifically for including contract addendums involving new government clients who require GCC High licenses. | Revision Needed | Complete | Pending | Complete | Pending
Government - Block of Hours - Actual Rates | GOV | NRR | Block of Hours (Actual Rates) | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - Block of Hours (Actual Rates) | Used for quoting government-related Non-Recurring Revenue (NRR) with actual rates over specified blocks of hours. | Revision Needed | Complete | Pending | Complete | Pending
Government - Block of Hours - Blended Rates | GOV | NRR | Block of Hours (Blended Rates) | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - Block of Hours (Blended Rates) | Used for quoting government Non-Recurring Revenue (NRR) using blended rates within designated blocks of hours. | Revision Needed | Complete | Pending | Complete | Pending
Government - Non-Recurring | GOV | NRR | Basic | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - Basic | Used for quoting basic government-related Non-Recurring Revenue (NRR). | Revision Needed | Complete | Pending | Complete | Pending
Government - Non-Recurring (Legacy Bronze) | GOV | NRR | Basic (Legacy Bronze) | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - Basic (Legacy Bronze) | Used for quoting government-related Non-Recurring Revenue (NRR) for customers at legacy bronze rates. (soon to be deprecated) | Revision Needed | Complete | Pending | Complete | Pending
Government - Renewal | GOV | NRR | Renewal | Standard |  | Keep | Revised | Temporary Deleted | GOV - NRR - Renewal | Utilized for the renewal of government-related Non-Recurring Revenue (NRR). | Revision Needed | Complete | Pending | Complete | Pending
HPE Warranty Renewals |  | NRR | - | Standard |  | Delete | Revised |  | - NRR - - |  | Approved | Approved | Approved | Approved | Approved
Network Infrastructure and Security Assessment Template - Paul Wartenberg |  | NRR | - | Standard |  | Delete | Revised |  | - NRR - - |  | Approved | Approved | Approved | Approved | Approved
Nimble Storage Support Renewal -1 Year |  | NRR | - | Standard |  | Delete | Revised |  | - NRR - - |  | Approved | Approved | Approved | Approved | Approved
Non-Recurring | MPC | NRR | Basic | Standard |  | Modify | Revised | Master Template | MPC - NRR - Basic | Used for quoting basic Non-Recurring Revenue (NRR). | Revision Needed | Complete | Pending | Complete | Pending
NRR - Communications - Cabling - NEW |  | NRR | - | Unknown |  | Delete | Revised |  | - NRR - - |  | Approved | Approved | Approved | Approved | Approved
OHD Master Quotes | MPC | NRR | OHD Master Quotes | Custom | JSobernheim | Modify | Revised | Waiting | MPC - NRR - Custom - JSobernheim - OHD Master Quotes | This custom template is specifically designed for Overhead Door, facilitating the management of Non-Recurring Revenue (NRR) through tailored master quotes. | Revision Needed | Complete | Pending | Complete | Pending
Physical Security - NRR | MPC | NRR | Physical Security | Standard |  | Modify | Revised | Waiting | MPC - NRR - Physical Security | Used for quoting Non-Recurring Revenue (NRR) associated with physical security services or products. | Revision Needed | Complete | Pending | Complete | Pending
Project to Replace Existing Firewall which is going End Of Service | MPC | NRR | Renewal Project (Firewall) | Custom | JSobernheim | Modify | Revised | Waiting | MPC - NRR - Custom - JSobernheim - Renewal Project (Firewall) | This custom template is designed for managing the renewal projects related to firewall services nearing the end of their service life. It focuses on the Non-Recurring Revenue (NRR) associated with updates, replacements, or extensions of firewall systems, ensuring continued protection and compliance with security standards. | Revision Needed | Complete | Pending | Complete | Pending
PSEC - Physical Security |  | NRR | - | Unknown |  | Delete |  |  | - NRR - - |  | Approved | Approved | Approved | Approved | Approved
Renewal | MPC | NRR | Renewal | Standard |  | Keep | Revised | Waiting | MPC - NRR - Renewal | Utilized for the renewal of Non-Recurring Revenue (NRR). | Revision Needed | Complete | Pending | Complete | Pending
Security Risk Assessment | MPC | NRR | Security Risk Assessment | Standard |  | Modify | Revised | Waiting | MPC - NRR - Security Risk Assessment | Originally developed for ReliableIT, this template is now utilized to quote Non-Recurring Revenue (NRR) for security risk assessments. | Revision Needed | Complete | Pending | Complete | Pending
VMS NRR - Fixed Labor Rates | VMS | NRR | Fixed Labor Rates | Unknown |  | Keep | Reach out to Mitch Verma to find out if these can be deprecated | Waiting | VMS - NRR - Fixed Labor Rates | Review | Revision Needed | Complete | Pending | Complete | Pending
VMS NRR - PSP Labor Rates | VMS | NRR | PSP Labor Rates | Unknown |  | Keep | Reach out to Mitch Verma to find out if these can be deprecated | Waiting | VMS - NRR - PSP Labor Rates | Review | Revision Needed | Complete | Pending | Complete | Pending
VMS Renewals | VMS | NRR | Renewal | Unknown |  | Keep | Reach out to Mitch Verma to find out if these can be deprecated | Waiting | VMS - NRR - Renewal | Review | Revision Needed | Complete | Pending | Complete | Pending
SSI-NRR-Basic-Standard | SSI | NRR | Basic | Standard |  | Modify | Revised | Waiting | SSI - NRR - Basic | Developed for SSI, this template is used for quoting basic Non-Recurring Revenue (NRR). | Revision Needed | Complete | Pending | Complete | Pending
1 Year MRR Subscription |  | UNKNOWN |  |  |  | TBD
AM - ESTIMATE |  | UNKNOWN |  |  |  | TBD
AM - Meriplex - MRR |  | UNKNOWN |  |  |  | TBD | Redundant to `Non-Recurring` template;
AM - Meriplex - MRR Cloud |  | UNKNOWN |  |  |  | TBD
Annual Upfront Pay - ARR |  | UNKNOWN |  |  |  | TBD | We use this for NRR Annual upfront pay for Microsoft 365, EP
Avita - New Site |  | UNKNOWN |  |  |  | TBD
Backup of AM - Microsoft 365 MASTER Agreement Additions |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Basic HW/SW Template |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Basic Quote Template |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
BB and SDWan |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Bluebeam License Subscription Addition |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Communications - SCI - IPT/Wireless/Switching |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Communications - Site Assessment |  | UNKNOWN |  |  |  | TBD | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Communications Additions/Addendum |  | UNKNOWN |  |  |  | TBD | Nobody uses it.
CPI - Products & Services Master v3 |  | UNKNOWN |  |  |  | TBD
CPI- NetManage and NetSecure - 2022 |  | UNKNOWN |  |  |  | TBD
Cyberian Managed Services Agreement |  | UNKNOWN |  |  |  | TBD
Datto S4 Business Continuity and Disaster Recovery (BCDR) Solution |  | UNKNOWN |  |  |  | TBD
Datto S5 Business Continuity and Disaster Recovery (BCDR) Solution |  | UNKNOWN |  |  |  | TBD
Detailed HW/SW Template |  | UNKNOWN |  |  |  | TBD | Check the terms tab and fields
Dial2Teams Template |  | UNKNOWN |  |  |  | TBD
DO NOT USE - Government M365 GCC High |  | UNKNOWN |  |  |  | TBD
Do Not Use - Meriplex Tab Templates |  | UNKNOWN |  |  |  | TBD
DO NOT USE Government - MSP A LA Cart 2.0 |  | UNKNOWN |  |  |  | TBD
DO NOT USE YET - Term Options |  | UNKNOWN |  |  |  | TBD
ESTIMATE |  | UNKNOWN |  |  |  | TBD
F1 Microsoft 365 NCE Subscription |  | UNKNOWN |  |  |  | TBD
F1 Project - Fixed Price |  | UNKNOWN |  |  |  | TBD
F1 Project - Fixed Price - Bronze |  | UNKNOWN |  |  |  | TBD
F1 Project - Fixed Price - Pre 2024 Gold/Silver/Hybrid |  | UNKNOWN |  |  |  | TBD
F1 Project - Time & Materials |  | UNKNOWN |  |  |  | TBD
F1 Project - Time & Materials - Bronze |  | UNKNOWN |  |  |  | TBD
Government - Meriplex Managed Microsoft M365+ Service (Commercial/Non-Profit) |  | UNKNOWN |  |  |  | TBD
Government - MRR - Change Order (CO)/Amendment/Renewal |  | UNKNOWN |  |  |  | TBD
Government MRR - STD |  | UNKNOWN |  |  |  | TBD
IaaS / DRaaS |  | UNKNOWN |  |  |  | TBD
IMO - White Label MSP Services |  | UNKNOWN |  |  |  | TBD
IMO-White Label MSP Services |  | UNKNOWN |  |  |  | TBD
John - PC |  | UNKNOWN |  |  |  | TBD
John - Shipping Costs |  | UNKNOWN |  |  |  | TBD
M365 - Annual Recurring |  | UNKNOWN |  |  |  | TBD
MCS3 |  | UNKNOWN |  |  |  | TBD
MCS3 - Amendment |  | UNKNOWN |  |  |  | TBD
Meriplex - MRR - Change Order (CO)/Amendment/Renewal |  | UNKNOWN |  |  |  | TBD
Meriplex Internal |  | UNKNOWN |  |  |  | TBD
Meriplex Managed Microsoft M365+ Service |  | UNKNOWN |  |  |  | TBD
Meriplex MSSP - Managed SIEM with Platinum Endpoint Protection |  | UNKNOWN |  |  |  | TBD
Microsoft 365 License Election - Acquisition Version |  | UNKNOWN |  |  |  | TBD
Microsoft 365 MASTER Agreement |  | UNKNOWN |  |  |  | TBD
Microsoft Copilot for Microsoft 365 |  | UNKNOWN |  |  |  | TBD
Microsoft MASTER Agreement Addition(s) |  | UNKNOWN |  |  |  | TBD
Microsoft Master Agreement Additions |  | UNKNOWN |  |  |  | TBD
Microsoft NCE Election Agreement |  | UNKNOWN |  |  |  | TBD
MRR - STD |  | UNKNOWN |  |  |  | TBD
MRR - STD |  | UNKNOWN |  |  |  | TBD
MRR - STD - Version 2 |  | UNKNOWN |  |  |  | TBD
MSP 2024 |  | UNKNOWN |  |  |  | TBD
MSP -A LA Cart 2.0 |  | UNKNOWN |  |  |  | TBD
MSP Input Template 2022 |  | UNKNOWN |  |  |  | TBD
MSP Input Template 2023 |  | UNKNOWN |  |  |  | TBD
MSP Test |  | UNKNOWN |  |  |  | TBD
New Microsoft Master Agreement |  | UNKNOWN |  |  |  | TBD
Next Gen Cloud |  | UNKNOWN |  |  |  | TBD
Next Gen Cyber Security Suite |  | UNKNOWN |  |  |  | TBD
Next Gen Managed IT |  | UNKNOWN |  |  |  | TBD
Northstar-MMRC- MSP & MSSP |  | UNKNOWN |  |  |  | TBD
ONI - Basic Quote Template |  | UNKNOWN |  |  |  | TBD
ONI - Basic Quote Template |  | UNKNOWN |  |  |  | TBD
ONI - Basic Quote Template |  | UNKNOWN |  |  |  | TBD
Per Service Ticket # 10549505 - Standard SSL Certificate For classicbevco.com |  | UNKNOWN |  |  |  | TBD
Per Service Ticket # 117342 - Zix Renewal - Annual Subscription |  | UNKNOWN |  |  |  | TBD
Plan Comparison Input 2023 |  | UNKNOWN |  |  |  | TBD
Project with Phases Converted |  | UNKNOWN |  |  |  | TBD
Recurring Block - Dollars per Month - Actual Labor Rates |  | UNKNOWN |  |  |  | TBD
Recurring Block - Hours Per Month - Blended Labor Rates |  | UNKNOWN |  |  |  | TBD
Reliable IT (RIT) IT/SRA Security Risk Assessment Template |  | UNKNOWN |  |  |  | TBD
SCI - MRR |  | UNKNOWN |  |  |  | TBD
Service Cancellation Letter |  | UNKNOWN |  |  |  | TBD
Solutions - Reorder MASTER TEMPLATE |  | UNKNOWN |  |  |  | TBD
System Template - Do Not Use - MSP Plan Comparison Layout |  | UNKNOWN |  |  |  | TBD
Test Template Order Porter Name |  | UNKNOWN |  |  |  | TBD
TrustX Staff Augmentation |  | UNKNOWN |  |  |  | TBD
UCaaS |  | UNKNOWN |  |  |  | TBD
UCaaS Contract Replacement MTM |  | UNKNOWN |  |  |  | TBD
Upgrade 510s to 620s - 3 sites |  | UNKNOWN |  |  |  | TBD
VMS MRR - Fixed Labor Rates |  | UNKNOWN |  |  |  | TBD
VMS MRR - PSP Labor Rates |  | UNKNOWN |  |  |  | TBD
VMS Tab Template (Do Not Use or Delete) |  | UNKNOWN |  |  |  | TBD
[9 empty] | Order Porter Template approval modification issue | send screenshots to Eric Dieckmann |  |  |  | Using Etilize Search | SFTP Pricing
[9 empty] | PDF Template modifications | gather NRR Team to |  |  |  |  | SFTP File Location
[9 empty] | Shipping costs | [5 empty] | SFTP Username
SFTP Password
NRR Global Rules (Master Template)
Audit trail on template changes or layout changes
Note on O2: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O3: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O5: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O6: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O7: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O8: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O9: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O10: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O11: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O12: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O13: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O14: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O18: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O20: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O21: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O22: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O24: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O25: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O26: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O27: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O28: Ian Wheeler: Name: 2024 Meriplex Standard
Note on O29: Ian Wheeler: Name: 2024 Meriplex Standard

## Changes Made
Change (Short Description) | Change (Long Description) | Impact | Approval | Documentation | Awareness | Training
Quote Templates Created | "NRR - Standard" Quote Templates have been created and now need joint collaboration and ongoing maintenance to account for edge case scenarios | Reduce Contract Errors

## Standard & Custom Fields
Field Name | Original Name | Short Name | Pod Name | Access | New Field Name | New Short Name | Reason for Change | Description
Api Status | Api Status
Approval Download Lock | Approval Download Lock
Approval Status | Approval Status
Approved Date | Approved Date
Credit Application Status | Credit Application Status
GreatAmerica Credit Application Status | GreatAmerica Credit Application Status
Hide Counter Signature Before Approval | Hide Counter Signature Before Approval
Post Status | Invoice Post Status
Is Approved | Is Approved
Lock Status | Lock Status
OP Approved | Order Porter Approved | OP Approved
Order Status | Order Status
Peer Review Status | Peer Review Status
Quote Status | Quote Status
Remote Approval Packet | Remote Approval Packet
Script Approval | Script Approval
Company | Account Name | Company
Contact Name | Contact Name
Customer Signature Capture | Customer Signature Capture
Customer Signature Capture Link | Customer Signature Capture Link
Has Contact Date | Has Contact Date
Customer ID: | Id Customers
Customer PO# | Purchase Order #
Account Executive | Z _custom Quote String 17 | Account Executive
Customer Account Name | Z _custom Quote String 23
Company Name: | Z _custom Quote String 24 | Company
MSA Company name | Z _custom Quote String 5
Custom Po # | Custom Po #
Default Opp Type | Default Opp Type
Default Tab Term Recurring Type | Default Recurring Term Type
Default Report List | Default Report List
Default Report Name | Default Report Name
Default Success Profile | Default Success Profile
Default Video List | Default Video List
GreatAmerica Default | GreatAmerica Default
Is Request Template | Is Request Template
Is Template | Is Template
Order Porter Template | Order Porter Template
Order Porter Template Destination | Order Porter Template Destination
Quickbooks Template | Quickbooks Template
Remote Template Name | Remote Template Name
Template Group | Template Group
Template Id | Template Id
Contract End Date | Contract End Date
Contract Start Date | Contract Start Date
Contract Term | Default Term Periods
Html Agreement | Html Agreement
Master Agreement | Master Agreement
Is Master Agreement | Z _custom Quote Bool 6 | Is Master Agreement
Meriplex Master Agreement# | Z _custom Quote String 4 | Master Agreement
Counter Signature Capture | Counter Signature Capture
Counter Signature Capture Link | Counter Signature Capture Link
Order Porter Show Signature | Order Porter Show Signature
MSA Signature Date | Z _custom Quote String 7
Deliver Document Type | Deliver Document Type
Order Porter Preview Picture | Order Porter Preview Picture
Order Porter Preview Picture Link | Order Porter Preview Picture Link
Peer Review Document | Peer Review Document
Peer Review Pdf Url | Peer Review Pdf Url
Review Email Peer Emails | Review Email Peer Emails
MRR Delta | Adjustment Amount 1 | MRR Delta
Delta - Test | Adjustment Amount 2 | MRR Delta
Adjustment Amount 3 | Adjustment Amount 3
Adjustment Amount 4 | Adjustment Amount 4
Expiring Agreement MRR | Adjustment Amount 5
Adjustment Percent 1 | Adjustment Percent 1
Adjustment Percent 2 | Adjustment Percent 2
Adjustment Percent Amount 1 | Adjustment Percent Amount 1
Adjustment Percent Amount 2 | Adjustment Percent Amount 2
Gross Margin | Gross Margin
Gross Margin Amount | Gross Margin Amount
Is MRR Renewal | Is Accepted | MRR Renewal
MRR Delta - Opp | Master Agreement #
Printed Gross Margin | Printed Gross Margin
Printed Gross Margin Amount | Printed Gross Margin Amount
Printed Recurring Gross Margin | Printed Recurring Gross Margin
Recurring Gross Margin | Recurring Gross Margin
Recurring Gross Margin Amount | Recurring Gross Margin Amount
MRR Subtotal | Recurring Subtotal | MRR Subtotal
Total Contract Value | Total Contract Value
Negative Delta | Z _custom Quote String 15 | Delta -
Positive Delta | Z _custom Quote String 9 | Delta +
Base Currency | Base Currency
Bo Version | Bo Version
Conversion Rate | Conversion Rate
Converted Currency | Converted Currency
Cost Changes | Cost Changes
Create Date | Create Date
Created From | Created From
Create Notes | Create Notes
Credit Application Id | Credit Application Id
Credit Application Source | Credit Application Source
Project ID: | Crm Project Id
Sales Order: | Crm Sales Order Id
Service Ticket: | Crm Service Ticket Id
Currency | Currency Culture
Cw Owned Forecast Ids | Cw Owned Forecast Ids
Delivered Date | Delivered Date
Docusign Envelope Id | Docusign Envelope Id
Embedded Video Html | Embedded Video Html
Enable Advanced Rounding | Enable Advanced Rounding
Expected Close Date | Expected Close Date
Exp Date | Expiration Date | Exp Date
External Reference | External Reference
GreatAmerica Credit Application Id | GreatAmerica Credit Application Id
Grid Format | Grid Format
G S T | G S T
Gst Converted | Gst Converted
Has Converted Rtf Images | Has Converted Rtf Images
Hide Cover Page | Hide Cover Page
Html Notes 1 | Html Notes 1
Html Notes 2 | Html Notes 2
Opp# | Id C R M Opportunity | Opp#
Campaign: | Id Source Campaign
Inside Rep | Inside Rep
Invoice Post Date | Invoice Post Date
Historical Version | Is Archive
Is Complete | Is Complete | Order Completed
Is New Logo | Is Create Demand | New Logo
Is Lost | Is Lost
Is Change Order | Is Order Porter Cacheable | Change Order
Is Order Porter First | Is Order Porter First
Is Order Porter Uploaded | Is Order Porter Uploaded
Is Renewal | Is Request Quote | Renewal
Is UpSell / XSell | Is Sent | Up-Sell / X-Sell
Is Standard Modification | Is Standard Modification
Keywords | Keywords
Last Success Time | Last Success Time
Long Description | Long Description
Lost Reason | Lost Reason
Markup | Markup
Modify Date | Modify Date
Months In Payment Schedule Table | Months In Payment Schedule Table
Net Margin | Net Margin
Ns Subsidiary | Ns Subsidiary
Optional Amount | Optional Amount
Optional Amount Converted | Optional Amount Converted
Order Porter Authnet | Order Porter Authnet
Order Porter Db Index | Order Porter Db Index
Order Porter Downpayment Minimum | Order Porter Downpayment Minimum
Order Porter Downpayment Percent | Order Porter Downpayment Percent
Order Porter Email Sig | Order Porter Email Sig
Order Porter Esign | Order Porter Esign
Order Porter Filtered Ip | Order Porter Filtered Ip
Order Porter First Visit Date | Order Porter First Visit Date
Order Porter Fullpayment | Order Porter Fullpayment
Order Porter Generated Pdf | Order Porter Generated Pdf
Tab Option Group | Tab Option Group
Order Porter Initials Sig | Order Porter Initials Sig
Order Porter Modified | Order Porter Modified
Order Porter Passcode | Order Porter Passcode
Order Porter Payment Mode | Order Porter Payment Mode
Order Porter Paypal | Order Porter Paypal
Order Porter Request Passcode | Order Porter Request Passcode
Order Porter Show Image | Order Porter Show Image
Order Porter Show Item Cb | Order Porter Show Item Cb
Order Porter Show Line Details | Order Porter Show Line Details
Order Porter Show Qty | Order Porter Show Qty
Order Porter Show Tab Cb | Order Porter Show Tab Cb
Order Porter Signed Date | Order Porter Signed Date | OP Signed Date
Order Porter Signed Date Utc | Order Porter Signed Date Utc
Order Porter Signed Ip | Order Porter Signed Ip
Order Porter Terms | Order Porter Terms
Order Porter Theme | Order Porter Theme
Order Porter Url | Order Porter Url
Order Porter Visits | Order Porter Visits
Override Rate | Override Rate
AE | Owner | AE
Bundle Show Header | Bundle Show Header
Bundle Show Items | Bundle Show Items
Payfabric Gateway Acct Name | Payfabric Gateway Acct Name
Pdf Merge Position | Pdf Merge Position
Picture | Picture
Picture Link | Picture Link
Printed Markup | Printed Markup
Printed Recurring Markup | Printed Recurring Markup
Probability | Probability
Product Search Prefill Mapping Set | Product Search Prefill Mapping Set
Promise Date | Promise Date
Promise Date Changes | Promise Date Changes
P S T | P S T
Pst Converted | Pst Converted
Published Pdf Url | Published Pdf Url
Publish Email Bcc | Publish Email Bcc
Publish Email Cc | Publish Email Cc
Publish Method | Publish Method
Publish # | Publish #
Publish Pdf Name | Publish Pdf Name
Quosal Purchasing Notes | Quosal Purchasing Notes
Recurring Cost | Recurring Cost
Recurring Gst | Recurring Gst
Recurring Markup | Recurring Markup
Recurring Net Margin | Recurring Net Margin
Recurring Optional Amount | Recurring Optional Amount
Recurring Override Rate | Recurring Override Rate
Recurring Pst | Recurring Pst
Recurring Suggested Total | Recurring Suggested Total
Recurring Total | Recurring Total
Report Uris | Report Uris
Order Date | Request Date | Order Date
Requested By | Requested By
Request Id | Request Id
Requires Name Change | Requires Name Change
Rtf Notes 1 | Rtf Notes 1
Rtf Notes 2 | Rtf Notes 2
Selected Terms Total | Selected Terms Total
Shipping Notes | Shipping Notes
Shipping Subtotal | Shipping Subtotal
Shipping Total | Shipping Total
Short Description | Short Description
NRR Subtotal | Subtotal | NRR Subtotal
Subtotal Converted | Subtotal Converted
Success Disabled | Success Disabled
Suggested Total | Suggested Total
Target Date | Target Date
Terms And Conditions | Terms And Conditions
Total Downpayment | Total Downpayment
Total Monthly Payments | Total Monthly Payments
Total Payment Amount | Total Payment Amount
Trial Tag | Trial Tag
Use Standard Publish Output | Use Standard Publish Output
Version | Version
Version Comment | Version Comment
Version Date | Version Date
Versioned By | Versioned By
Win Form | Win Form
Win Tab Fail | Win Tab Fail
Win Tab Pass | Win Tab Pass
Win Tab Warning | Win Tab Warning
Won Lost Date | Won Lost Date
Show Cover Page | Z _custom Quote Bool 1
No Show Bundle Qty | Z _custom Quote Bool 10 | No Show Bundle Qty
Show Terms Table Layout | Z _custom Quote Bool 2
Show "No Pricing" Layout | Z _custom Quote Bool 4
Is Communications | Z _custom Quote Bool 5 | Communications
Service Addresses Mapped | Z _custom Quote Bool 7 | Service Addresses Ma
Is NRR Renewal | Z _custom Quote Bool 8 | NRR Renewal
Is Negative | Z _custom Quote Bool 9
Master Renewal True Up Date | Z _custom Quote Date 1 | True Up Date
Service Ticket # | Z _custom Quote String 1
Total Recurring Payments | Z _custom Quote String 10
Note for Procurement | Z _custom Quote String 11 | Note for Procurement
Processed By | Z _custom Quote String 12 | Processed By
Reorder Ship To | Z _custom Quote String 13
Additional Notes: | Z _custom Quote String 14 | Additional Notes
SC | Z _custom Quote String 16 | Strategic Consultant
Pre-Sales Coordinator | Z _custom Quote String 18 | PSC
Your Title: | Z _custom Quote String 19 | Your Title:
Payment Schedule | Z _custom Quote String 2
Strategic Consultant | Z _custom Quote String 20 | Strategic Consultant
Principal Technologist | Z _custom Quote String 21 | Principal Technologi
Physical Sec Architect | Z _custom Quote String 22 | Physical Sec Archite
Additional Note(s): | Z _custom Quote String 25 | Additional Note(s):
Terms and Conditions Options | Z _custom Quote String 28
Meriplex SO # | Z _custom Quote String 3
Your Name: | Z _custom Quote String 30 | Your Name:
Internal Quoting Notes | Z _custom Quote String 8
Opportunity Grouping Default | Connectwise Op Group
Id Quote Main | Id Quote Main
Is Api Quote | Is Api Quote
Items Have Quote Id | Items Have Quote Id
Quoted By: | Modify User Name | Quoted By:
Original Quote Id | Original Quote Id
Quote Audio | Quote Audio
Quote Audio Data | Quote Audio Data
Quote Audio Hashcode | Quote Audio Hashcode
Quote Audio Type | Quote Audio Type
Quote Cost | Quote Cost
Quote Data Url | Quote Data Url
Quote Name | Quote Name
Quote Notes | Quote Notes
Quote Preface | Quote Preface
Quote Price Modifier | Quote Price Modifier
Quote# | Quote Readable Id | Quote#
Quote Recurring Price Modifier | Quote Recurring Price Modifier
Quote Time Zone | Quote Time Zone
Quote Total | Quote Total
Quote Total Converted | Quote Total Converted
Quote Type | Quote Type
Quote Video | Quote Video
Quote Video Data | Quote Video Data
Quote Video Hashcode | Quote Video Hashcode
Quote Video Type | Quote Video Type
Remote Opportunity Id | Remote Opportunity Id
Web Quote Available | Web Quote Available
2. Vendor/ Mfr Quote# | Web Quote # | Vendor/ Mfr Quote#
Z _custom Quote Date 2 | Z _custom Quote Date 2
Z _custom Quote Decimal 1 | Z _custom Quote Decimal 1
Z _custom Quote Decimal 10 | Z _custom Quote Decimal 10
Z _custom Quote Decimal 11 | Z _custom Quote Decimal 11
Z _custom Quote Decimal 12 | Z _custom Quote Decimal 12
Z _custom Quote Decimal 13 | Z _custom Quote Decimal 13
Z _custom Quote Decimal 14 | Z _custom Quote Decimal 14
Z _custom Quote Decimal 15 | Z _custom Quote Decimal 15
Z _custom Quote Decimal 16 | Z _custom Quote Decimal 16
Z _custom Quote Decimal 17 | Z _custom Quote Decimal 17
Z _custom Quote Decimal 18 | Z _custom Quote Decimal 18
Z _custom Quote Decimal 19 | Z _custom Quote Decimal 19
Z _custom Quote Decimal 2 | Z _custom Quote Decimal 2
Z _custom Quote Decimal 20 | Z _custom Quote Decimal 20
Z _custom Quote Decimal 3 | Z _custom Quote Decimal 3
Z _custom Quote Decimal 4 | Z _custom Quote Decimal 4
Z _custom Quote Decimal 5 | Z _custom Quote Decimal 5
Z _custom Quote Decimal 6 | Z _custom Quote Decimal 6
Z _custom Quote Decimal 7 | Z _custom Quote Decimal 7
Z _custom Quote Decimal 8 | Z _custom Quote Decimal 8
Z _custom Quote Decimal 9 | Z _custom Quote Decimal 9
Z _custom Quote String 26 | Z _custom Quote String 26
Z _custom Quote String 27 | Z _custom Quote String 27
Z _custom Quote String 29 | Z _custom Quote String 29
Z _custom Quote String 6 | Z _custom Quote String 6
All Tax | All Tax
Default Price List | Default Price List
Discount Amount | Discount Amount
Discount Amount Converted | Discount Amount Converted
Include Zero Suggested In Discount | Include Zero Suggested In Discount
Is Tax Calculated | Is Tax Calculated
Bundle Print Header Price | Bundle Print Header Price
Bundle Print Item Price | Bundle Print Item Price
Price Changes | Price Changes
Price Level | Price Level
Printed Recurring Suggested Discount Percent | Printed Recurring Suggested Discount Percent
Printed Suggested Discount Percent | Printed Suggested Discount Percent
Recurring All Tax | Recurring All Tax
Recurring Discount Amount | Recurring Discount Amount
Recurring Suggested Discount Amount | Recurring Suggested Discount Amount
Recurring Tax | Recurring Tax
Shipping Tax | Shipping Tax
Suggested Discount Amount | Suggested Discount Amount
Tax | Tax
Tax Code | Tax Code
Tax Converted | Tax Converted
Tax Rate | Tax Rate
Cache Duration Time | Cache Duration Time
Cache Expire Date | Cache Expire Date
Location | Location Id
Order Porter Cache | Order Porter Cache
Invoice Post User Id | Invoice Post User Id | Invoice Post User Id
User Id | User Id | Quote Creator
Show Service & Billing Information Block | Z _custom Quote Bool 3

## Dropdown Keys
PROJECT TRACKER
DROPDOWN KEYS
TASK STATUSES | PRIORITY | TEMPLATE STATUSES | Dropdown | Dropdown | Dropdown | Dropdown | Dropdown | Dropdown | Dropdown | Dropdown
Not Started | Low | Not Started
In Progress | Medium | In Progress
Complete | High | Complete
Revision Needed |  | Revision Needed
Approved |  | Approved
Overdue |  | Overdue
On Hold |  | On Hold

## Quote Templates (Feedback)
Quote Template Name | Company ID | Category | Template Description | Type | CreatedBy | Action | Description | New Quote Template Name | Notes | Michael True | Shaun Kilkenny | Anthony Kazlauskas | Jackie Moore | Jerry Prestridge | John Sobernheim | Laura Emery | Brian McShane | Cynthia Newsom | Ron Walker | Shaun Kilkenny2 | Anthony Kazlauskas3
AM - Block of Hours - Actual Rates | MPC | NRR | Block of Hours (Actual Rates) | Standard |  | Modify | Used for NRR Actual Rates Block of Hours Fixed hours block time Recommend merge with blended rates and consolidate products or add additional tab | MPC - NRR - Block of Hours (Actual Rates) | Used for NRR Actual Rates Block of Hours | [7 empty] | TBD
AM - Block of Hours - Blended Rates | MPC | NRR | Block of Hours (Blended Rates) | Standard |  | Keep | Initially created by AM's for their specific needs. Recommend merge with actual rates and consolidate products or add additional tab Used for NRR Blended Rates Block of Hours | MPC - NRR - Block of Hours (Blended Rates) | Initially created by AM's for their specific needs. Used for NRR Blended Rates Block of Hours |  |  | Keep |  |  | Keep |  | TBD | Keep |  |  | Keep
AM - NRR |  | NRR | - | Standard |  | Delete | Training/descriptive template | - NRR - - | Training/descriptive template |  |  | Keep |  |  |  |  | TBD | Keep |  |  | Keep
AM - Time and Materials (TnM) - STD | MPC | NRR | Time and Materials (TnM) | Standard |  | Keep | Time and Materials | MPC - NRR - Time and Materials (TnM) | Time and Materials | [5 empty] | Keep |  | TBD | Keep
Annual NRR Upfront Pay | MPC | NRR | Upfront (Annual) Pay | Standard |  | Modify | Paying for annual licenses upfront | MPC - NRR - Upfront (Annual) Pay | Paying for annual licenses upfront |  |  |  | Keep | Keep |  |  | TBD
Change Order | MPC | HYBRID | Change Order | Standard |  | Modify | Change Order | MPC - HYBRID - Change Order | Change Order |  | Keep | Keep | Keep | Keep | Keep |  | TBD |  |  | Keep | Keep
F1 GCC High Licenses - Add On Orders | GOV | NRR | GCC High Licenses (Add On Orders) | Standard |  | Keep | Pro-rated pricing for additional licenses needed by the client | GOV - NRR - GCC High Licenses (Add On Orders) | Pro-rated pricing for additional licenses needed by the client | [6 empty] | Keep | TBD
F1 GCC High Licenses / Contract - Addendum | GOV | NRR | GCC High Licenses (Contract Addendum) | Standard |  | Keep | A new GCC high-client (addendum tab added for products needed after the initial contract has been provisioned) | GOV - NRR - GCC High Licenses (Contract Addendum) | A new GCC high-client (addendum tab added for products needed after the initial contract has been provisioned) | [6 empty] | Keep | TBD
Government - Block of Hours - Actual Rates | GOV | NRR | Block of Hours (Actual Rates) | Standard |  | Keep | Used for GOV NRR Actual Rates Block of Hours | GOV - NRR - Block of Hours (Actual Rates) | Userd for GOV NRR Actual Rates Block of Hours | [5 empty] | Keep | Keep | TBD
Government - Block of Hours - Blended Rates | GOV | NRR | Block of Hours (Blended Rates) | Standard |  | Keep | Used for GOV NRR Blended Rates Block of Hours | GOV - NRR - Block of Hours (Blended Rates) | Used for GOV NRR Blended Rates Block of Hours | [5 empty] | Keep | Keep | TBD
Government - Non-Recurring | GOV | NRR | Basic | Standard |  | Keep | GOV Non-Recurring | GOV - NRR - Basic | GOV Non-Recurring | [5 empty] | Keep | Keep | TBD
Government - Non-Recurring (Legacy Bronze) | GOV | NRR | Basic (Legacy Bronze) | Standard |  | Keep | Bronze rates customers. Future deprecation | GOV - NRR - Basic (Legacy Bronze) | Bronze rates customers. Future deprecation | [5 empty] | Keep | Keep | TBD
Government - Renewal | GOV | NRR | Renewal | Standard |  | Keep | GOV Renewal | GOV - NRR - Renewal | GOV Renewal | [6 empty] | Keep | TBD
HPE Warranty Renewals |  | NRR | - | Standard |  | Delete |  | - NRR - - | [8 empty] | TBD
Network Infrastructure and Security Assessment Template - Paul Wartenberg |  | NRR | - | Standard |  | Delete |  | - NRR - - | [8 empty] | TBD
Nimble Storage Support Renewal -1 Year |  | NRR | - | Standard |  | Delete |  | - NRR - - | [8 empty] | TBD
Non-Recurring | MPC | NRR | Basic | Standard |  | Modify | Non-Recurring; copying over client details and signed information. | MPC - NRR - Basic | Non-Recurring |  | Keep | Keep | Keep | Keep | Keep | Keep | Keep |  |  | Keep | Keep
NRR - Communications - Cabling - NEW |  | NRR | - | Unknown |  | Delete |  | - NRR - - | [8 empty] | TBD | Keep
OHD Master Quotes | MPC | NRR | OHD Master Quotes | Custom | JSobernheim |  | Built for Overhead Door | MPC - NRR - Custom - JSobernheim - OHD Master Quotes | Built for Overhead Door |  |  |  | Keep |  |  |  | TBD
Physical Security - NRR | MPC | NRR | Physical Security | Standard |  | Modify | Physical Security | MPC - NRR - Physical Security | Physical Security |  |  |  | Keep |  |  |  | TBD
Project to Replace Existing Firewall which is going End Of Service | MPC | NRR | Renewal Project (Firewall) | Custom | JSobernheim | Modify | for Firewall end of service | MPC - NRR - Custom - JSobernheim - Renewal Project (Firewall) | for Firewall end of service | [5 empty] | Keep |  | TBD
PSEC - Physical Security |  | NRR | - | Unknown |  | Delete |  | - NRR - - | [8 empty] | TBD
Renewal | MPC | NRR | Renewal | Standard |  | Keep | NRR Renewal | MPC - NRR - Renewal | NRR Renewal |  |  |  | Keep | Keep | Keep |  | TBD
Security Risk Assessment | RIT | NRR | Security Risk Assessment | Standard |  | Modify | NRR Security Risk Assessment; Standardize the verbiage, and modify so the Order Porter, Grid Layout, and PDF reflect Meriplex standards. | RIT - NRR - Security Risk Assessment | NRR Security Risk Assessment | [7 empty] | TBD
VMS NRR - Fixed Labor Rates | VMS | NRR | Fixed Labor Rates | Unknown |  | TBD | Reach out to Mitch Verma to find out if these can be deprecated | VMS - NRR - Fixed Labor Rates | [8 empty] | TBD
VMS NRR - PSP Labor Rates | VMS | NRR | PSP Labor Rates | Unknown |  | TBD | Reach out to Mitch Verma to find out if these can be deprecated | VMS - NRR - PSP Labor Rates | [8 empty] | TBD
VMS Renewals | VMS | NRR | Renewal | Unknown |  | TBD | Reach out to Mitch Verma to find out if these can be deprecated | VMS - NRR - Renewal | [8 empty] | TBD
SSI-NRR-Basic-Standard | SSI | NRR | Basic | Standard |  | Modify |  | SSI - NRR - Basic
1 Year MRR Subscription |  | UNKNOWN
AM - ESTIMATE |  | UNKNOWN
AM - Meriplex - MRR |  | UNKNOWN |  |  |  |  | Redundant to `Non-Recurring` template;
AM - Meriplex - MRR Cloud |  | UNKNOWN
Annual Upfront Pay - ARR |  | UNKNOWN |  |  |  |  | We use this for NRR Annual upfront pay for Microsoft 365, EP
Avita - New Site |  | UNKNOWN
Backup of AM - Microsoft 365 MASTER Agreement Additions |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Basic HW/SW Template |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Basic Quote Template |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
BB and SDWan |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Bluebeam License Subscription Addition |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Communications - SCI - IPT/Wireless/Switching |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Communications - Site Assessment |  | UNKNOWN |  |  |  |  | Discuss with Wes Brown what stylistic changes and changes overall can be made.
Communications Additions/Addendum |  | UNKNOWN |  |  |  |  | Nobody uses it.
CPI - Products & Services Master v3 |  | UNKNOWN
CPI- NetManage and NetSecure - 2022 |  | UNKNOWN
Cyberian Managed Services Agreement |  | UNKNOWN
Datto S4 Business Continuity and Disaster Recovery (BCDR) Solution |  | UNKNOWN
Datto S5 Business Continuity and Disaster Recovery (BCDR) Solution |  | UNKNOWN
Detailed HW/SW Template |  | UNKNOWN |  |  |  |  | Check the terms tab and fields
Dial2Teams Template |  | UNKNOWN
DO NOT USE - Government M365 GCC High |  | UNKNOWN
Do Not Use - Meriplex Tab Templates |  | UNKNOWN
DO NOT USE Government - MSP A LA Cart 2.0 |  | UNKNOWN
DO NOT USE YET - Term Options |  | UNKNOWN
ESTIMATE |  | UNKNOWN
F1 Microsoft 365 NCE Subscription |  | UNKNOWN
F1 Project - Fixed Price |  | UNKNOWN
F1 Project - Fixed Price - Bronze |  | UNKNOWN
F1 Project - Fixed Price - Pre 2024 Gold/Silver/Hybrid |  | UNKNOWN
F1 Project - Time & Materials |  | UNKNOWN
F1 Project - Time & Materials - Bronze |  | UNKNOWN
Government - Meriplex Managed Microsoft M365+ Service (Commercial/Non-Profit) |  | UNKNOWN
Government - MRR - Change Order (CO)/Amendment/Renewal |  | UNKNOWN
Government MRR - STD |  | UNKNOWN
IaaS / DRaaS |  | UNKNOWN
IMO - White Label MSP Services |  | UNKNOWN
IMO-White Label MSP Services |  | UNKNOWN
John - PC |  | UNKNOWN
John - Shipping Costs |  | UNKNOWN
M365 - Annual Recurring |  | UNKNOWN
MCS3 |  | UNKNOWN
MCS3 - Amendment |  | UNKNOWN
Meriplex - MRR - Change Order (CO)/Amendment/Renewal |  | UNKNOWN
Meriplex Internal |  | UNKNOWN
Meriplex Managed Microsoft M365+ Service |  | UNKNOWN
Meriplex MSSP - Managed SIEM with Platinum Endpoint Protection |  | UNKNOWN
Microsoft 365 License Election - Acquisition Version |  | UNKNOWN
Microsoft 365 MASTER Agreement |  | UNKNOWN
Microsoft Copilot for Microsoft 365 |  | UNKNOWN
Microsoft MASTER Agreement Addition(s) |  | UNKNOWN
Microsoft Master Agreement Additions |  | UNKNOWN
Microsoft NCE Election Agreement |  | UNKNOWN
MRR - STD |  | UNKNOWN
MRR - STD |  | UNKNOWN
MRR - STD - Version 2 |  | UNKNOWN
MSP 2024 |  | UNKNOWN
MSP -A LA Cart 2.0 |  | UNKNOWN
MSP Input Template 2022 |  | UNKNOWN
MSP Input Template 2023 |  | UNKNOWN
MSP Test |  | UNKNOWN
New Microsoft Master Agreement |  | UNKNOWN
Next Gen Cloud |  | UNKNOWN
Next Gen Cyber Security Suite |  | UNKNOWN
Next Gen Managed IT |  | UNKNOWN
Northstar-MMRC- MSP & MSSP |  | UNKNOWN
ONI - Basic Quote Template |  | UNKNOWN
ONI - Basic Quote Template |  | UNKNOWN
ONI - Basic Quote Template |  | UNKNOWN
Per Service Ticket # 10549505 - Standard SSL Certificate For classicbevco.com |  | UNKNOWN
Per Service Ticket # 117342 - Zix Renewal - Annual Subscription |  | UNKNOWN
Plan Comparison Input 2023 |  | UNKNOWN
Project with Phases Converted |  | UNKNOWN
Recurring Block - Dollars per Month - Actual Labor Rates |  | UNKNOWN
Recurring Block - Hours Per Month - Blended Labor Rates |  | UNKNOWN
Reliable IT (RIT) IT/SRA Security Risk Assessment Template |  | UNKNOWN
SCI - MRR |  | UNKNOWN
Service Cancellation Letter |  | UNKNOWN
Solutions - Reorder MASTER TEMPLATE |  | UNKNOWN
System Template - Do Not Use - MSP Plan Comparison Layout |  | UNKNOWN
Test Template Order Porter Name |  | UNKNOWN
TrustX Staff Augmentation |  | UNKNOWN
UCaaS |  | UNKNOWN
UCaaS Contract Replacement MTM |  | UNKNOWN
Upgrade 510s to 620s - 3 sites |  | UNKNOWN
VMS MRR - Fixed Labor Rates |  | UNKNOWN
VMS MRR - PSP Labor Rates |  | UNKNOWN
VMS Tab Template (Do Not Use or Delete) |  | UNKNOWN